# Project Planning and Management Plan

AI Interview Preparation Agent | DEPI Project | Version 1.0 | October 2026

## 1. Project Overview

The AI Interview Preparation Agent is an agentic AI platform that simulates a realistic job interview for a candidate based on a specific job opportunity. The user provides a job URL or a job description file and, optionally, a CV. The system analyzes the job requirements and the candidate profile, identifies skill gaps, builds a personalized interview plan, conducts an adaptive interview (text or voice), evaluates every answer, and finally produces a detailed performance report with a personalized learning roadmap.

Unlike a chatbot that generates static questions, the platform is built as a multi-agent system. A central Orchestrator Agent coordinates specialized agents (Job Analyzer, Candidate Analyzer, Interview Planner, Adaptive Interviewer, Answer Evaluator, Learning Agent, Report Generator) and gives them access to tools such as web search, a job page reader, a RAG knowledge base, speech-to-text and text-to-speech. Short-term and long-term memory allow the system to remember previous interviews and adapt future preparation.

## 2. Project Objectives

- Build an end-to-end platform that turns a job posting and a CV into a personalized, adaptive mock interview.

- Evaluate each answer on multiple dimensions (technical accuracy, completeness, communication, relevance, problem solving) and give actionable feedback.

- Adapt question difficulty and topic selection in real time based on candidate performance.

- Track progress across interviews using long-term memory and generate personalized learning plans.

- Demonstrate core Agentic AI concepts: orchestration, tool use, function calling, memory, RAG, planning and decision making.

- Deliver a working system, full documentation, testing evidence and a final presentation by 4 December 2026.

## 3. Scope

### 3.1 In Scope

- Job input via URL, PDF, TXT or DOCX, and optional CV upload with structured parsing.

- Job analysis, candidate analysis and gap analysis.

- Interview planning, adaptive questioning, follow-up questions and behavioral (STAR-based) evaluation.

- Answer evaluation with scores, feedback and a suggested better answer.

- Optional voice interview using speech-to-text and text-to-speech.

- RAG knowledge base of interview questions and concepts.

- Short-term and long-term memory, interview history and progress tracking.

- Learning resource search, learning plan and final report.

- Web dashboard with performance charts.

### 3.2 Out of Scope

- Native mobile applications.

- Integration with real employer hiring systems or applicant tracking systems.

- Video-based analysis of facial expressions or body language.

- Guaranteeing real interview outcomes or acting as a recruitment decision tool.

## 4. Deliverables and Milestones

The following deliverables and deadlines are set by the DEPI program schedule.

| Deliverable | Deadline |
| --- | --- |
| Project Planning and Management | 16 Oct 2026 |
| Literature Review | 16 Oct 2026 |
| Requirements Gathering | 16 Oct 2026 |
| System Analysis and Design | 6 Nov 2026 |
| Implementation (Source Code and Execution) | 30 Nov 2026 |
| Final Presentation, Testing and Reports | 4 Dec 2026 |

## 5. Work Breakdown and Timeline

The project runs for about eight weeks, from early October to 4 December 2026, in five phases.

| Phase | Main Activities | Period | Output |
| --- | --- | --- | --- |
| 1. Initiation and Planning | Define vision, scope, team roles, tools, risks and schedule | 1 - 16 Oct | This plan |
| 2. Research and Requirements | Literature review, competitor analysis, requirements gathering, user stories | 1 - 16 Oct | Literature review, SRS |
| 3. Analysis and Design | Architecture, agent design, database schema, API design, UI wireframes, prompt and tool design | 17 Oct - 6 Nov | Design document, diagrams |
| 4. Implementation | Backend, agents, RAG, memory, voice, frontend and integration, in three sprints | 7 - 30 Nov | Working system |
| 5. Testing, Reporting and Presentation | Functional and agent evaluation testing, bug fixing, final report, demo preparation | 24 Nov - 4 Dec | Test report, final presentation |

### 5.1 Implementation Sprints

| Sprint | Dates | Goals |
| --- | --- | --- |
| Sprint 1 | 7 - 14 Nov | Project skeleton, database, job and CV input, Job Analyzer, Candidate Analyzer, gap analysis |
| Sprint 2 | 15 - 22 Nov | Interview Planner, Adaptive Interviewer, Answer Evaluator, RAG knowledge base, memory |
| Sprint 3 | 23 - 30 Nov | Learning Agent, Report Generator, dashboard, voice interview, integration and bug fixing |

### 5.2 Gantt Chart

Gantt chart · 9 rows, 1 milestone

Planning, literature review and requirements run in parallel until 16 Oct; design follows until 6 Nov, then three build sprints, with testing and the final presentation closing on 4 Dec.

## 6. Team Structure and Responsibilities

The team members and exact allocation are to be completed by the team. A suggested split of roles is shown below.

| Role | Responsibilities | Assigned To |
| --- | --- | --- |
| Project Manager / Scrum Master | Planning, tracking, meetings, risk follow-up | [Name] |
| AI / Agents Engineer | Orchestrator, agents, prompts, tool calling | [Name] |
| RAG and Data Engineer | Knowledge base, embeddings, vector database, memory | [Name] |
| Backend Engineer | FastAPI services, PostgreSQL, authentication, APIs | [Name] |
| Frontend Engineer | Dashboard, interview screen, charts, voice UI | [Name] |
| QA and Documentation | Test cases, evaluation, reports, presentation | [Name] |

## 7. Task Assignment

Every deliverable has a clear owner and a due date; the owners are roles from the table above, and names will be filled in by the team.

| Task | Phase | Owner (role) | Due |
| --- | --- | --- | --- |
| Project proposal, plan, risk plan and KPIs | Planning | Project Manager | 16 Oct 2026 |
| Literature review of agents, RAG, memory and evaluation | Research | AI / Agents Engineer, RAG and Data Engineer | 16 Oct 2026 |
| Requirements, personas, user stories and validation survey | Requirements | QA and Documentation, Project Manager | 16 Oct 2026 |
| Architecture, use case, DFD, sequence, activity, state and class diagrams | Analysis and Design | AI / Agents Engineer, Backend Engineer | 6 Nov 2026 |
| ER diagram, logical and physical schema | Analysis and Design | Backend Engineer | 6 Nov 2026 |
| Agent prompts, tool schemas and orchestration graph design | Analysis and Design | AI / Agents Engineer | 6 Nov 2026 |
| UI/UX wireframes, mockups and guidelines | Analysis and Design | Frontend Engineer | 6 Nov 2026 |
| Backend APIs, authentication and database | Implementation | Backend Engineer | 30 Nov 2026 |
| Job and candidate analyzers, gap analysis, planner, adaptive interviewer, evaluator | Implementation | AI / Agents Engineer | 30 Nov 2026 |
| RAG knowledge base, embeddings and memory | Implementation | RAG and Data Engineer | 30 Nov 2026 |
| Dashboard, interview screen, charts | Implementation | Frontend Engineer | 30 Nov 2026 |
| Voice interview (speech-to-text and text-to-speech) | Implementation | AI / Agents Engineer, Frontend Engineer | 30 Nov 2026 |
| Test plan, test cases, automated tests and bug reports | Testing | QA and Documentation (all members fix bugs) | 4 Dec 2026 |
| User manual, technical documentation, README, presentation and demo video | Final reports | QA and Documentation, Project Manager | 4 Dec 2026 |
| Upload every document and the source code to GitHub | All phases | Project Manager | At each deadline |

## 8. Resource Allocation

### 8.1 Human Resources

Effort level of each role in every phase (High, Medium, Low):

| Role | Planning and Research | Analysis and Design | Implementation | Testing and Reports |
| --- | --- | --- | --- | --- |
| Project Manager / Scrum Master | High | Medium | Medium | High |
| AI / Agents Engineer | Medium | High | High | Medium |
| RAG and Data Engineer | Medium | Medium | High | Medium |
| Backend Engineer | Low | High | High | Medium |
| Frontend Engineer | Low | Medium | High | Medium |
| QA and Documentation | High | Medium | Medium | High |

### 8.2 Tools and Infrastructure

| Resource | Purpose | Source |
| --- | --- | --- |
| GitHub | Version control, documentation, issues and project board | Free |
| Task board (GitHub Projects or similar) | Sprint and task tracking | Free |
| LLM API | Agents, question generation and evaluation | Paid usage or credits; usage limits set during testing |
| Speech-to-text and text-to-speech APIs | Voice interview | Free tier or paid usage |
| Web search API | Company research and learning resources | Free tier or paid usage |
| PostgreSQL and vector store | Application data, memory and RAG | Run locally or in containers; free |
| Hosting for the demo | Deployed version of the web app | Free tier or a low-cost cloud instance |
| Team laptops | Development and testing | Owned by team members |

### 8.3 Budget

The main cost is API usage (LLM, speech and search). The team will use free tiers and credits where possible, cache repeated calls, and set a usage cap during testing. The final estimate will be confirmed once the API providers are chosen in the design phase.

## 9. Methodology

The team follows an Agile, sprint-based approach adapted to the short DEPI timeline. Planning and design phases are completed first, then implementation is split into one-week sprints with a short planning session at the start and a review at the end. Progress is tracked on a shared task board with the states To Do, In Progress, In Review and Done. A short weekly meeting reviews progress, blockers and next steps.

## 10. Technology Stack

| Area | Technology |
| --- | --- |
| Backend | Python, FastAPI |
| Agent framework | LangGraph (primary option), LangChain; CrewAI as an alternative |
| Relational database | PostgreSQL |
| Vector database | A vector store such as pgvector, Qdrant or Chroma (final choice during design) |
| LLM | LLM API with structured outputs and function calling |
| Speech | Speech-to-text and text-to-speech APIs |
| Web search | Web search API for company and learning resource research |
| Frontend | Web dashboard (React or a similar framework) |
| Collaboration | GitHub for version control, a shared task board, shared documentation |

## 11. Risk Assessment and Mitigation Plan

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Short timeline versus a large feature set | High | High | Prioritize features (MoSCoW); voice and company research are optional stretch goals |
| R2 | LLM hallucination or inconsistent evaluation scores | Medium | High | Structured outputs, scoring rubrics, RAG grounding, test set of sample answers |
| R3 | Job page scraping fails or is blocked | Medium | Medium | Fallback to file upload or pasted text |
| R4 | API cost and rate limits | Medium | Medium | Caching, smaller models for simple tasks, usage limits during testing |
| R5 | Latency in voice interview | Medium | Medium | Streaming where possible; text mode as default |
| R6 | Integration problems between agents | Medium | High | Clear state schema, early integration in Sprint 1, regular end-to-end tests |
| R7 | Handling personal data in CVs | Low | High | Store only what is needed, secure storage, clear user consent and deletion option |
| R8 | Team member unavailability | Low | Medium | Shared documentation, pair work on critical modules |

## 12. Key Performance Indicators

The project is measured against the following targets; they will be checked during testing and reported in the final report.

| Category | KPI | Target | How It Is Measured |
| --- | --- | --- | --- |
| Performance | Response time for the next question | 10 seconds or less for 95% of questions | Timing logs during test interviews |
| Reliability | System uptime during testing and demo | 95% or higher | Monitoring and error logs |
| Accuracy | Required skills correctly extracted from job postings | 90% or higher on a set of 20 test postings | Manual comparison with a reference list |
| Evaluation quality | Score consistency when the same answer is scored repeatedly | Difference of 1 point or less out of 10 | Repeated scoring of a set of sample answers |
| Adaptation | Test scenarios where difficulty changes correctly (up after strong answers, down after weak ones) | 90% or higher | Scripted scenarios with strong and weak answers |
| Personalization | Weak skills from a previous interview reflected in the next plan | 100% of test cases | Two-interview test scenarios |
| Code quality | Unit test coverage of core modules | 70% or higher | Coverage report |
| User adoption | Testers who complete at least one full interview | At least 20 testers | Usage records |
| User satisfaction | Average tester rating of usefulness | 4 out of 5 or higher | Feedback form |
| Delivery | DEPI deliverables submitted on time | 6 of 6 | Submission dates |
| Delivery | Planned sprint tasks completed | 80% or higher per sprint | Task board |

## 13. Quality Assurance

- Code reviews through pull requests before merging.

- Unit tests for parsers, tools and database operations.

- Integration tests for the full flow from job input to final report.

- Agent evaluation: a set of sample answers (strong, average and weak) to check that scoring is consistent and difficulty adapts correctly.

- User acceptance testing with a small group of student testers before the final presentation.

## 14. Communication Plan

| Activity | Frequency | Purpose |
| --- | --- | --- |
| Team stand-up or sync | Twice a week | Progress and blockers |
| Sprint planning and review | Weekly during implementation | Goals and demo of finished work |
| Mentor meeting | As scheduled by DEPI | Feedback and approvals |
| Task board update | Daily | Transparency |

## 15. Success Criteria

- The system completes the full workflow: job input, analysis, gap analysis, adaptive interview, evaluation, report and learning plan.

- Question difficulty visibly adapts to answer quality in test scenarios.

- Memory is demonstrated by using a previous interview to influence the next one.

- All six DEPI deliverables are submitted on or before their deadlines.

- The final presentation includes a live demo and the system architecture.